## Functional Requirments
Page | Details | Owner | IB Status | Murthy ji Team Status | ETA | Content | Comments
Home
| Banner |  | Open | Open |  |  | We will share the content shortly
| What is Innovat Bharat? |  | Closed | Open
| Vision and Mission |  | Closed
| What We Do |  | Closed | Open
| Problem & Reality |  | Closed | Open
| Students |  | Closed | Open |  |  | It has to be redirected to new inner page
| Mentors |  | Open | Open |  |  | It has to be redirected to new inner page
| Collaborate : Company , Instistutes , NGO |  | Closed | Open |  |  | It has to be redirected to new inner page
| Testimonials (Students, Mentors, Colleges) |  | Open | Open |  |  | This section need to be removed
| Contact Us |  | Open | Open
| Quote of the day |  | Open | Open |  |  | will change everyday - I will share the content shortly
About
| Why Innovat Bharat |  | Closed
| Our Mission and Our Vision |  | Closed | Open
| Core Values |  | Closed | Open
| Our team |  | Open | Open
For Colleges
| College Registration |  | Open | Open
| College List? Place holder | [5 empty] | We will keep it in Future
Collaborate
| Company Registration |  | Open | Open
| NGOs Registration |  | Open | Open
| Collaborators List?? |  | Open | Open |  |  | We will keep it in future
Events/Sessions | [6 empty] | Just put a place holder
| Events List Upcoming and Past Events |  | Open | Open
| Registration Form |  | Open | Open
| Payment Setup for Paid Events |  | Open | Open |  |  | remove this section
| Email Notification |  | Open | Open
|  |  | Open | Open
Membership
| Membership Details |  | Enabled | Open |  |  | remove this section
| Membersip Form |  | Working | Open |  |  | remove this section
| Payment Setup for Paid Members |  | Working | Open |  |  | remove this section
| Email Notification |  | Working | Open |  |  | remove this section
| Member profile , login , registration , Discounts for events |  | Open | Open |  |  | remove this section
| life time membership | [5 empty] | remove this section
| annual membership | [5 empty] | remove this section
| term membership | [5 empty] | remove this section
Donations
| Donation Campaign , Details |  | Open | Open |  |  | remove this section
| Donation Form |  | Open | Open |  |  | remove this section
| Payment Setup |  | Open | Open |  |  | remove this section
| Email Notification |  | Open | Open |  |  | remove this section
Get Involved
| Volunteer Oppurtunities |  | Enabled | Open
Contact Us
| Contact Details Page |  | Enabled | Open
| Google Map location |  | Enabled | Open |  |  | remove this section
Footer
| About Us |  | Enabled | Open
| Contact |  | Enabled | Open
| Gallery |  | Enabled | Open
| Volunteer |  | Enabled | Open
| Member |  | Enabled | Open
| Events/Sessions |  | Enabled | Open
| Social Media Channels |  | Enabled | Open
Web Solution Enablement Tasks
| Kick-Off Meeting |  | Enabled
| Requirements Discussion |  | Enabled
| Visual Design |  | Open
| Base Solution |  | Open
| Solution QA |  | Open
| Functional Coverage Review |  | Open
| SSL Certificate |  | Open
| Domain Linking |  | Open
| Final Solution |  | Open
| GO Live |  | Open